## GASKET
材料管制單
訂購編號：20250923-002 |  |  | 日期: 2025年 09月 23日 | [11 empty] | 合約數量 |  |  | 採購數量
Item | 品名 | Size | Description | Unit | 工業級數量 | 消防數量 | 洗滌塔數量 | VER.2數量 | 地下管數量 | 臨時數量 | 12/4數量 | 1/9數量 | 1/15數量 | 小計數量 | 工業級數量 | 消防數量 | TOTAL數量 | 數量 (庫存) | 數量 (9/23) | 數量 (9/24) | 數量 (11/04) | 數量 (12/04) | 數量 (1/9) | 數量 (1/9) | 累計採購數量 | 差異數量 | 累計收料 | 收料數量 (10/3) | 收料數量 (10/13) | 收料數量 (01/16)
1 | GASKET | GR-1/2"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 29 |  |  | 33 | [5 empty] | 33 | 29 |  | 29 | 29 | 0 | 0 | 4 |  |  |  | 4 | 0 | 4 |  | 4
2 | GASKET | GR-3/4"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 174 |  |  | 174 | [5 empty] | 174 | 174 |  | 174 | 129 | 45 | 0 |  |  |  |  | 45 | 0 | 45 | 45
3 | GASKET | GR-1"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 458 |  |  | 480 | [5 empty] | 480 | 453 |  | 453 | 38 | 420 | 11 | 11 |  |  |  | 442 | 0 | 442 | 431 | 11
4 | GASKET | GR-1.1/2"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 127 |  |  | 128 | [5 empty] | 128 | 127 |  | 127 | 91 | 36 | 3 |  |  |  |  | 39 | 0 | 39 | 39
5 | GASKET | GR-1.1/4"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 3 |  |  | 1 | [5 empty] | 1 | 3 |  | 3 |  | 3 | 0 |  |  |  |  | 3 | 0 | 3 | 3
6 | GASKET | GR-2"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 207 |  |  | 212 |  |  | 4 |  |  | 216 | 193 |  | 193 | 40 | 167 | 17 |  |  |  |  | 184 | 0 | 184 | 184
7 | GASKET | GR-3"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 127 |  |  | 132 | [5 empty] | 132 | 117 |  | 117 | 105 | 22 | 9 |  |  |  |  | 31 | 0 | 31 | 31
8 | GASKET | GR-4"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 142 |  |  | 142 |  |  | 6 |  |  | 148 | 139 |  | 139 |  | 142 | 3 |  | 3 |  |  | 148 | -3 | 145 | 145
9 | GASKET | GR-6"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 40 |  |  | 41 | [5 empty] | 41 | 41 |  | 41 | 15 | 25 | 0 | 1 |  |  |  | 26 | 0 | 26 | 25 | 1
10 | GASKET | GR-8"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 4 |  |  | 4 | [5 empty] | 4 | 4 |  | 4 | 1 | 3 | 0 |  |  |  |  | 3 | 0 | 3 | 3
11 | GASKET | GR-10"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 1 |  |  | 1 | [5 empty] | 1 | 1 |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 0 | 0
12 | GASKET | GR-12"-ZW#7500 | GASKET 150# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 3 |  |  | 3 | [5 empty] | 3 | 3 |  | 3 | 1 | 2 | 0 |  |  |  |  | 2 | 0 | 2 | 2
13 | GASKET | GR-1/2" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 3 |  | 2 | 2 | [5 empty] | 4 | 3 |  | 3 | 3 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1
14 | GASKET | GR-3/4" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 3 |  | 2 | 9 | [5 empty] | 11 | 3 |  | 3 | 3 | 0 | 6 | 2 |  |  |  | 8 | 0 | 8 | 6 | 2
15 | GASKET | GR-1" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 31 | 6 | 6 | 30 | [5 empty] | 42 | 31 | 6 | 37 |  | 37 | 0 | 5 |  |  |  | 42 | 0 | 42 | 37 | 5
16 | GASKET | GR-1.1/2" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 5 |  | 7 | 5 | [5 empty] | 12 | 1 |  | 1 | 5 | 0 | 4 | 3 |  |  |  | 7 | 0 | 7 | 4 | 3
17 | GASKET | GR-2" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 27 | 1 | 2 | 29 | [5 empty] | 32 | 25 | 1 | 26 | 28 | 0 | 4 |  |  |  |  | 4 | 0 | 4 | 4
18 | GASKET | GR-2.1/2" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC |  | 12 |  | 2 | [5 empty] | 14 |  | 12 | 12 |  | 12 | 0 | 2 |  |  |  | 14 | 0 | 14 | 12 | 2
19 | GASKET | GR-3" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 26 |  | 1 | 26 | [5 empty] | 27 | 27 |  | 27 |  | 26 | 0 | 1 |  |  |  | 27 | 0 | 27 | 26 | 1
20 | GASKET | GR-4" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 49 | 5 | 1 | 49 |  |  | 1 |  |  | 56 | 48 | 5 | 53 | 49 | 5 | 1 |  | 1 |  |  | 7 | -1 | 6 | 6
21 | GASKET | GR-6" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 20 | 33 |  | 20 | [5 empty] | 53 | 20 | 33 | 53 |  | 53 | 0 |  |  |  |  | 53 | 0 | 53 | 53
22 | GASKET | GR-8" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 6 | 12 |  | 6 | [5 empty] | 18 | 6 | 12 | 18 |  | 18 | 0 |  |  |  |  | 18 | 0 | 18 | 18
23 | GASKET | GR-10" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC |  | 2 | [7 empty] | 2 |  | 2 | 2 |  | 2 | 0 |  |  |  |  | 2 | 0 | 2 | 2
24 | GASKET | GR-12" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 2 | 17 |  | 2 | [5 empty] | 19 | 2 | 17 | 19 |  | 19 | 0 |  |  |  |  | 19 | 0 | 19 | 19
25 | GASKET | GR-14" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 2 | 22 | 1 | 2 | [5 empty] | 25 | 2 | 22 | 24 |  | 24 | 0 | 1 |  |  |  | 25 | 0 | 25 | 24 | 1
26 | GASKET | GR-16" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC |  | 4 | [7 empty] | 4 |  | 4 | 4 |  | 4 | 0 |  |  |  |  | 4 | 0 | 4 | 4
27 | GASKET | GR-18" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC |  | 6 | [7 empty] | 6 |  | 6 | 6 | 1 | 5 | 0 |  |  |  |  | 5 | 0 | 5 | 5
28 | GASKET | GR-24" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC |  | 5 | [7 empty] | 5 |  | 5 | 5 |  | 5 | 0 |  |  |  |  | 5 | 0 | 5 | 5
29 | GASKET | GR-1/2" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 87 | 46 | 2 | 88 | [5 empty] | 136 | 86 | 55 | 141 | 86 | 47 | 1 | 2 |  |  |  | 50 | 0 | 50 | 48 | 2
30 | GASKET | GR-3/4" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 166 | 2 |  | 168 | [5 empty] | 170 | 164 | 2 | 166 | 22 | 146 | 4 |  |  |  |  | 150 | 0 | 150 | 150
31 | GASKET | GR-1" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 267 | 1 | 23 | 307 | [5 empty] | 331 | 268 | 1 | 269 | 43 | 225 | 33 | 30 |  |  |  | 288 | 0 | 288 | 258 | 30
32 | GASKET | GR-1.1/2" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 102 |  | 1 | 107 |  |  | 3 |  |  | 111 | 92 |  | 92 | 43 | 59 | 15 |  |  |  |  | 74 | 0 | 74 | 74
33 | GASKET | GR-2" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 245 | 107 | 6 | 262 | 14 |  |  | 2 |  | 391 | 240 | 137 | 377 | 111 | 241 | 19 | 18 |  | 2 |  | 280 | 0 | 280 | 260 | 18 | 2
34 | GASKET | GR-2.1/2" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 8 | 75 |  | 8 | [5 empty] | 83 | 8 | 93 | 101 |  | 83 | 0 |  |  |  |  | 83 | 0 | 83 | 83
35 | GASKET | GR-20" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 5 |  |  | 5 | [5 empty] | 5 | 5 |  | 5 | 5 | 0 | 0 |  |  |  |  | 0 | 0 | 0
36 | GASKET | GR-3" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 223 | 27 | 9 | 247 | 5 |  |  | 8 |  | 296 | 229 | 27 | 256 | 39 | 211 | 16 | 22 |  | 8 |  | 257 | 0 | 257 | 227 | 22 | 8
37 | GASKET | GR-4" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 182 | 50 | 6 | 178 | 14 |  | 8 | 6 | 34 | 296 | 179 | 50 | 229 | 232 | 0 | 1 | 15 |  | 14 | 34 | 64 | 0 | 64 | 1 | 15 | 48
38 | GASKET | GR-5" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 8 |  |  | 8 | [5 empty] | 8 | 8 |  | 8 |  | 8 | 0 |  |  |  |  | 8 | 0 | 8 | 8
39 | GASKET | GR-6" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 131 | 32 |  | 129 | 9 |  |  |  |  | 170 | 127 | 32 | 159 | 24 | 139 | 2 | 5 |  |  |  | 146 | 0 | 146 | 141 | 5
40 | GASKET | GR-8" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 47 | 12 |  | 48 | 4 |  |  |  |  | 64 | 47 | 12 | 59 | 30 | 29 | 1 | 4 |  |  |  | 34 | 0 | 34 | 30 | 4
41 | GASKET | GR-10" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 18 |  |  | 18 | [5 empty] | 18 | 18 |  | 18 | 4 | 14 | 0 |  |  |  |  | 14 | 0 | 14 | 14
42 | GASKET | GR-12" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 4 |  |  | 4 | [5 empty] | 4 | 4 |  | 4 | 1 | 3 | 0 |  |  |  |  | 3 | 0 | 3 | 3
43 | GASKET | GR-14" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC | 10 |  |  | 10 | [5 empty] | 10 | 10 |  | 10 |  | 10 | 0 |  |  |  |  | 10 | 0 | 10 | 10
44 | GASKET | GR3-1"-ZW#7500 | GASKET 300# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 2 |  |  | 2 | [5 empty] | 2 | 2 |  | 2 |  | 2 | 0 |  |  |  |  | 2 | 0 | 2 | 2
45 | GASKET | GR3-1.1/4"-ZW#7500 | GASKET 300# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 2 |  |  | 4 | [5 empty] | 4 | 2 |  | 2 |  | 2 | 0 | 2 |  |  |  | 4 | 0 | 4 | 2 | 2
46 | GASKET | GR3-2"-ZW#7500 | GASKET 300# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 4 |  |  | 4 | [5 empty] | 4 | 4 |  | 4 |  | 4 | 0 |  |  |  |  | 4 | 0 | 4 | 4
47 | GASKET | GR3-3"-ZW#7500 | GASKET 300# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 1 |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  | 1 | 0 |  |  |  |  | 1 | 0 | 1 | 1
48 | GASKET | GR3-4"-ZW#7500 | GASKET 300# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 1 |  |  | 1 | [5 empty] | 1 | 1 |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 0 | 0
49 | GASKET | GR3-8"-ZW#7500 | GASKET 300# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 1 |  |  | 1 | [5 empty] | 1 | 1 |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 0 | 0
50 | GASKET | GR3-12"-ZW#7500 | GASKET 300# RF 3.0 MM THICK VIRGIN PTFE ZW#7500 ASME B16.21/B16.5 | PC | 1 |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  | 1 | 0 |  |  |  |  | 1 | 0 | 1 | 1
51 | GASKET | GR-1/2" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 1 |  |  | 2 | [5 empty] | 2 | 1 |  | 1 | 1 | 0 | 1 |  |  |  |  | 1 | 0 | 1 | 1
52 | GASKET | GR-3/4" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 9 |  |  | 8 | [5 empty] | 8 | 9 |  | 9 | 9 | 0 | 0 |  |  |  |  | 0 | 0 | 0
53 | GASKET | GR-1" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 11 |  |  | 11 | [5 empty] | 11 | 12 |  | 12 | 11 | 0 | 0 |  |  |  |  | 0 | 0 | 0
54 | GASKET | GR-1.1/2" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 5 |  |  | 5 | [5 empty] | 5 | 5 |  | 5 | 5 | 0 | 0 |  |  |  |  | 0 | 0 | 0
55 | GASKET | GR-2" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 11 |  |  | 13 | [5 empty] | 13 | 11 |  | 11 | 11 | 0 | 0 | 2 |  |  |  | 2 | 0 | 2 |  | 2
56 | GASKET | GR-3" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 17 |  |  | 17 | [5 empty] | 17 | 17 |  | 17 | 13 | 4 | 0 |  |  |  |  | 4 | 0 | 4 | 4
57 | GASKET | GR-4" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 18 |  |  | 20 | [5 empty] | 20 | 18 |  | 18 | 18 | 0 | 2 |  |  |  |  | 2 | 0 | 2 | 2
58 | GASKET | GR-6" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC | 7 |  |  | 6 | [5 empty] | 6 | 7 |  | 7 | 7 | 0 | 0 |  |  |  |  | 0 | 0 | 0
59 | GASKET | GR-1/2" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS OUTER RING ASME B16.20/B16.5 | PC | 4 |  |  | 4 | [5 empty] | 4 |  |  | 0 |  | 4 | 0 |  |  |  |  | 4 | 0 | 4 | 4
60 | GASKET | GR-1" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS OUTER RING ASME B16.20/B16.5 | PC | 2 |  |  | 2 | [5 empty] | 2 |  |  | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 2 | 2 | 2
61 | GASKET | GF-2.1/2" | GASKET 150# FF 3.0 MM THICK COMP. NON-ASB. SYNTHETIC FIBER W/NBR BINDER ASME B16.21/B16.5 | PC |  | 1 |  |  | 12 |  |  |  |  | 13 |  | 1 | 1 | 1 | 0 | 0 | 12 |  |  |  | 12 | 6 | 18 | 6 | 12
62 | GASKET | GF-12" | GASKET 150# FF 3.0 MM THICK COMP. NON-ASB. SYNTHETIC FIBER W/NBR BINDER ASME B16.21/B16.5 | PC |  | 2 | [7 empty] | 2 |  | 2 | 2 | 2 | 0 | 0 |  |  |  |  | 0 | 5 | 5 | 5
63 | GASKET | GF-16" | GASKET 150# FF 3.0 MM THICK COMP. NON-ASB. SYNTHETIC FIBER W/NBR BINDER ASME B16.21/B16.5 | PC |  | 2 | [7 empty] | 2 |  | 2 | 2 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0
64 | GASKET | GR-1.1/4" | GASKET 150# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/SS304 OUTER RING ASME B16.20/B16.5 | PC |  |  |  | 1 | [5 empty] | 1 |  | 2 | 2 | 2 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1
65 | GASKET | GR-8" | GASKET 300# RF 4.5 MM THICK 304SS SPIRAL WOUND W/GRAPHITE FILLER W/CS OUTER RING ASME B16.20/B16.5 | PC |  |  |  | 1 | [5 empty] | 1 |  | 2 | 2 | 2 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1
66 | GASKET | GF-4" | GASKET 150# FF 3.0 MM THICK COMP. NON-ASB. SYNTHETIC FIBER W/NBR BINDER ASME B16.21/B16.5 | PC |  |  |  |  | 1 |  |  |  |  | 1 |  | 2 | 2 | 2 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1
67 | GASKET | GF-6" | GASKET 150# FF 3.0 MM THICK COMP. NON-ASB. SYNTHETIC FIBER W/NBR BINDER ASME B16.21/B16.5 | PC |  |  |  |  | 6 |  |  |  |  | 6 |  | 2 | 2 | 2 | 0 | 0 | 6 |  |  |  | 6 | 0 | 6 |  | 6
68 | GASKET | GR-1" | GASKET 150# RF 3 MM THICK 非石綿 | PC | [5 empty] | 7 |  |  |  | 7 |  | 2 | 2 | 2 | 0 | 0 | 7 |  |  |  | 7 | 0 | 7 |  | 7
69 | GASKET | GR-1.1/4" | GASKET 150# RF 3 MM THICK 非石綿 | PC | [5 empty] | 1 |  |  |  | 1 |  | 2 | 2 | 2 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1
70 | GASKET | GR-1.1/2" | GASKET 150# RF 3 MM THICK 非石綿 | PC | [5 empty] | 60 |  |  |  | 60 |  | 2 | 2 | 2 | 0 | 0 | 60 |  |  |  | 60 | 0 | 60 |  | 60
71 | GASKET | GR-2" | GASKET 150# RF 3 MM THICK 非石綿 | PC | [5 empty] | 9 |  |  |  | 9 |  | 2 | 2 | 2 | 0 | 0 | 9 |  |  |  | 9 | 0 | 9 |  | 9
72 | GASKET | GR-6" | GASKET 150# RF 3 MM THICK 非石綿 | PC | [5 empty] | 41 |  |  |  | 41 |  | 2 | 2 | 2 | 0 | 0 | 41 |  |  |  | 41 | 0 | 41 |  | 41
73 | GASKET | GR-14" | GASKET 150# RF 3 MM THICK 非石綿 | PC | [5 empty] | 1 |  |  |  | 1 |  | 2 | 2 | 2 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1
74 | GASKET | GR-16" | GASKET 150# RF 3 MM THICK 非石綿 | PC | [5 empty] | 2 |  |  |  | 2 |  | 2 | 2 | 2 | 0 | 0 | 2 |  |  |  | 2 | 0 | 2 |  | 2
75 | GASKET | GR-24" | GASKET 150# RF 3 MM THICK 非石綿 | PC | [5 empty] | 1 |  |  |  | 1 |  | 2 | 2 | 2 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1
76 | GASKET | GR-1.1/4" | GASKET 300# RF 3 MM THICK 非石綿 | PC | [5 empty] | 2 |  |  |  | 2 |  | 2 | 2 | 2 | 0 | 0 | 2 |  |  |  | 2 | 0 | 2 |  | 2
77 | GASKET | GR-1.1/2" | GASKET 300# RF 3 MM THICK 非石綿 | PC | [5 empty] | 1 |  |  |  | 1 |  | 2 | 2 | 2 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1
78 | GASKET | GR-3" | GASKET 300# RF 3 MM THICK 非石綿 | PC | [5 empty] | 6 |  |  |  | 6 |  | 2 | 2 | 2 | 0 | 0 | 6 |  |  |  | 6 | 0 | 6 |  | 6
79 | GASKET | GR-4" | GASKET 300# RF 3 MM THICK 非石綿 | PC | [5 empty] | 6 |  |  |  | 6 |  | 2 | 2 | 2 | 0 | 0 | 6 |  |  |  | 6 | 0 | 6 |  | 6
80 | GASKET | GR-6" | GASKET 300# RF 3 MM THICK 非石綿 | PC | [5 empty] | 2 |  |  |  | 2 |  | 2 | 2 | 2 | 0 | 0 | 2 |  |  |  | 2 | 0 | 2 |  | 2
81 | GASKET | GR-8" | GASKET 300# RF 3 MM THICK 非石綿 | PC | [5 empty] | 2 |  |  |  | 2 |  | 2 | 2 | 2 | 0 | 0 | 2 |  |  |  | 2 | 0 | 2 |  | 2
82 | GASKET | GR-12" | GASKET 300# RF 3 MM THICK 非石綿 | PC | [5 empty] | 1 |  |  |  | 1 |  | 2 | 2 | 2 | 0 | 0 | 1 |  |  |  | 1 | 0 | 1 |  | 1